## DAIR Log
Description | Item Type | Status | Date Identified | Date Due (if applicable) | Date Closed | D3 Phase | BU's impacted | Originator | Owned By | Impact (1 Low; 3 High) | Trending (1 Low; 3 High) | Attention Level (1 Low; 3 High) | Strategy (if applicable) | Impact On Project | Action Taken | Modified | Modified By
Store 2 years of incident data | Decision | Closed | 2019-10-09 | 2019-10-09 | 2019-10-09 | 1 | SHDR | John Mariotti | Nitin Bhatnagar | 1 | 1 | 1 | None | No impact |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Exclude for SHDR D3: Genetec, Easy Lobby, TRIRIGA, Office 365 | Decision | Closed | 2019-10-09 | 2019-10-19 | 2019-10-19 | 1 | SHDR | John Mariotti | Nitin Bhatnagar | 3 | 2 | 6 | Revisit at requirements gathering | Less scope of work |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Include SHDR project tasks in timeline | Action Item | Closed | 2019-10-23 | 2019-10-25 | 2019-11-12 | 1 | All | Catherine Kirkland | Nitin Bhatnagar | 2 | 1 | 2 |  |  |  | 2019-11-18 14:13 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting with Mary Boyd for EDH | Action Item | Closed | 2019-11-07 | 2019-11-08 | 2019-11-08 | 1 |  | Anthony Leung | Nitin Bhatnagar | 1 | 1 | 1 |  |  |  | 2019-11-13 10:47 | nitin.x.bhatnagar.-nd@disney.com
Prepare D3 UI mockups to present intended look-and-feel and some basic navigation for the target state system | Action Item | Closed | 2019-10-21 | 2019-11-11 | 2019-11-11 | 1 | All | Liz Robert, Rebecca Mamos | Catherine Kirkland | 1 | 2 | 2 |  |  |  | 2019-11-13 13:10 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting with Harold Cubillos, John Clarke, Elton Palmer, Shiraz Moti for EDH (Tech) | Action Item | Closed | 2019-11-07 | 2019-11-11 | 2019-11-11 | 1 |  | Anthony Leung | Nitin Bhatnagar | 1 | 1 | 1 |  |  |  | 2019-11-13 10:47 | nitin.x.bhatnagar.-nd@disney.com
Meet Tom Blanchard | Action Item | Open | 2019-11-07 | 2019-11-11 |  | 1 | All | Anthony Leung | Anthony Leung | 1 | 1 | 1 |  |  |  | 2019-11-08 10:19 | nitin.x.bhatnagar.-nd@disney.com
Schedule meetings for Soft Kick Off - series | Action Item | Closed | 2019-10-24 | 2019-11-12 | 2019-11-12 | 1 | All | Nitin Bhatnagar | Anthony Leung | 2 | 1 | 2 | Invitee list: |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting for Formal Kick Off | Action Item | Closed | 2019-10-24 | 2019-11-12 | 2019-11-12 | 1 | All | Nitin Bhatnagar | Anthony Leung | 2 | 1 | 2 | Invitee list: |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Schedule meetings for Business Requirement Gathering - series | Action Item | Closed | 2019-10-24 | 2019-11-12 | 2019-11-12 | 1 | All | Nitin Bhatnagar | Anthony Leung | 2 | 1 | 2 | Invitee list: |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting with Sandeep Sharma for Rostr | Action Item | Closed | 2019-11-07 | 2019-11-12 | 2019-11-12 | 1 |  | Anthony Leung | Nitin Bhatnagar | 1 | 1 | 1 |  |  |  | 2019-11-13 10:47 | nitin.x.bhatnagar.-nd@disney.com
Discuss and finalize D3 connectivity using Mutual SSL and WebVan | Action Item | Open | 2019-11-13 | 2019-11-13 |  | 1 | All | John Clarke, Michael Burch | John Clarke | 1 | 1 | 1 |  | Tech requirements timeline |  | 2019-11-13 13:52 | nitin.x.bhatnagar.-nd@disney.com
Update D3 connectivity Arch diagram | Action Item | Open | 2019-11-13 | 2019-11-15 |  | 1 | All | John Clarke, Michael Burch | John Clarke | 1 | 1 | 1 |  | Tech requirements timeline |  | 2019-11-13 16:58 | john.clarke@disney.com
Check on ISA requirement | Action Item | Open | 2019-11-13 | 2019-11-15 |  | 1 | All | John Clarke, Michael Burch | Nitin Bhatnagar | 1 | 1 | 1 |  | Tech requirements timeline |  | 2019-11-13 13:57 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting for Technical Kick Off | Action Item | Closed | 2019-10-24 | 2019-11-14 | 2019-11-14 | 1 | All | Nitin Bhatnagar | Nitin Bhatnagar | 2 | 1 | 2 | Invitee list: |  |  | 2019-11-18 14:09 | nitin.x.bhatnagar.-nd@disney.com
Add Dee Seymour and Sandeep Sharma from Rostr to D3 Teams group | Action Item | Closed | 2019-11-14 | 2019-11-14 | 2019-11-14 | 1 | All | Anthony Leung | Nitin Bhatnagar | 1 | 1 | 1 |  | Tech requirements timeline |  | 2019-11-14 12:39 | nitin.x.bhatnagar.-nd@disney.com
Add an updated Architecture Visio diagram to the D3 Microsoft Teams group and share the link with Dee, Sandeep and the project team | Action Item | Closed | 2019-11-14 | 2019-11-14 | 2019-11-14 | 1 | All | John Clarke | John Clarke | 1 | 1 | 1 |  | Tech requirements timeline |  | 2019-11-14 13:31 | nitin.x.bhatnagar.-nd@disney.com
Work with Edward Reese and Will / Colin to find out the recipient of each Event-type notification for each Group in RIMS | Action Item | Open | 2019-11-07 | 2019-11-15 |  | 1 | GSCC WCOPs | Catherine Kirkland | Shelagh Sayers | 2 | 1 | 2 |  | Requirements completion impacted | 11/12: Shelagh planning to meet with GSCC and WCOps today. | 2019-11-13 13:17 | nitin.x.bhatnagar.-nd@disney.com
Define Fox D3 data to migrate (fields and records) | Action Item | Open | 2019-11-11 | 2019-11-15 |  | 1 | Fox GSI | Anthony Leung | Shelagh Sayers | 3 | 1 | 3 |  |  |  | 2019-11-13 14:31 | nitin.x.bhatnagar.-nd@disney.com
Set up meeting with John Spiker to find out about EDH-TRIRIGA connectivity | Action Item | Closed | 2019-11-13 | 2019-11-15 | 2019-11-16 | 1 | All | John Clarke, Nitin Bhatnagar | Nitin Bhatnagar | 1 | 1 | 1 |  | Tech requirements timeline |  | 2019-11-18 14:14 | nitin.x.bhatnagar.-nd@disney.com
Submit Rostr intake form - mention we require access to personal pronouns (with employee images) for HRIS approval | Action Item | Closed | 2019-11-12 | 2019-11-18 | 2019-11-18 | 1 | All | Mary Boyd | Shiraz Moti | 2 | 1 | 2 |  | Tech team engagement |  | 2019-11-18 13:34 | nitin.x.bhatnagar.-nd@disney.com
Delay in contract signing will delay the project | Risk | Open | 2019-10-24 | 2019-11-19 |  | 1 | All | Anthony Leung | Anthony Leung | 2 | 1 | 2 | Mitigate - Drive legal teams from Disney and D3 to work on a mutually acceptable MSA document. Involve Business stakeholders to help with decision-making | Delay in project start |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Submit EDH engagement form for D3 integration | Action Item | Open | 2019-11-18 | 2019-11-20 |  | 1 | All | Anthony Leung | Shiraz Moti | 2 | 1 | 2 |  | Tech team engagement |  | 2019-11-18 14:14 | nitin.x.bhatnagar.-nd@disney.com
Submit EDH engagement form for TRIRIGA integration | Action Item | Open | 2019-11-18 | 2019-11-20 |  | 1 | All | Anthony Leung | Shiraz Moti | 2 | 1 | 2 |  | Tech team engagement |  | 2019-11-18 14:14 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting for Business Executive Committee - monthly | Action Item | Open | 2019-10-24 | 2019-11-22 |  | 1 | All | Liz Robert, Rebecca Mamos | Nitin Bhatnagar | 2 | 1 | 2 | Start with bimonthly initially and then change to monthly. Invitee list: John Raucci, Andrea Cunningham, Will Salazar, Alex Rodriguez, Liz Robert, Rebecca Mamos, Shelagh Sayers, Anthony Leung, Catherine Kirkland |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting for Steering Committee - monthly | Action Item | Open | 2019-10-24 | 2019-11-22 |  | 1 | All | Nitin Bhatnagar | Nitin Bhatnagar | 2 | 1 | 2 | Invitee list: Ron Iden, John Raucci, Liz Robert, Nancy Faginas-Cody, Andrea Cunningham, Rebecca Mamos, Shelagh Sayers, Anthony Leung, Catherine Kirkland |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Schedule meeting for Operating Committee - weekly | Action Item | Open | 2019-10-24 | 2019-11-22 |  | 1 | All | Nitin Bhatnagar | Nitin Bhatnagar | 2 | 1 | 2 | Invitee list: Rodrigo Amigorena, Liz Robert, Rebecca Mamos, Shelagh Sayers, Anthony Leung, Catherine Kirkland, John Clarke, John Mariotti |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Schedule meetings for Technical Requirement - series | Action Item | Open | 2019-10-24 | 2019-11-22 |  | 1 | All | Nitin Bhatnagar | Nitin Bhatnagar | 2 | 1 | 2 | Invitee list: |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Prepare Locations info in spreadsheet format with alias info as suggested by Liz | Action Item | In Progress | 2019-11-11 | 2019-11-22 |  | 1 | GSCC GSI SHDR WCOPs | Anthony Leung | Catherine Kirkland | 2 | 1 | 2 |  |  |  | 2019-11-13 13:10 | nitin.x.bhatnagar.-nd@disney.com
Prepare Kick Off slide deck | Action Item | In Progress | 2019-10-18 | 2019-11-25 |  | 1 | All | Anthony Leung | Nitin Bhatnagar | 3 | 2 | 6 |  |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Finalize Kick Off deck and route for review with Rebecca, ... | Action Item | Open | 2019-11-07 | 2019-11-25 |  | 1 | All | Anthony Leung | Nitin Bhatnagar | 2 | 1 | 2 |  |  |  | 2019-11-13 14:31 | nitin.x.bhatnagar.-nd@disney.com
Follow up on GIS Advisory Review with Harold Cubillos | Action Item | Open | 2019-11-18 | 2019-11-25 |  | 1 | All | Harold Cubillos | Nitin Bhatnagar | 2 | 1 | 2 |  | Project Data Architecture |  | 2019-11-18 13:31 | nitin.x.bhatnagar.-nd@disney.com
Business requirements and collaboration with Genetec and Easy Lobby teams | Risk | Open | 2019-11-01 | 2019-12-02 |  | 1 | All | Anthony Leung | Anthony Leung | 3 | 1 | 3 |  |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Liz to get information on the wireless radio integrated with the CAD system in use by Anaheim PD. Context: DLR and Aulani plan to use Motorola LEX-11 wireless radios for security officers. These radios have GPS, touchscreen, cameras and PTT | Action Item | Open | 2019-10-10 | 2020-01-15 |  | 2 | Aulani DLR | Tina Ramirez | Liz Robert | 2 | 1 | 2 |  |  |  | 2019-11-18 14:07 | nitin.x.bhatnagar.-nd@disney.com
Latency for Dispatch form – creating, editing, assigning officers and saving | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung | Nitin Bhatnagar | 3 | 1 | 3 | Mitigate - Vendor to monitor capacity of SaaS environment and the application, and make adjustment if needed; add legal language to require key performance metrics; add milestone for response time acceptance | Latency will impact critical dispatch operations at the communications center |  | 2019-11-13 10:41 | anthony.leung@disney.com
Business Operations Impact – a new dispatch system will impact a key operation of security | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung | Liz Robert | 3 | 1 | 3 | Mitigate - Conduct proof of concept sessions to ensure critical business requirements are met; provide robust training for dispatch staff and officers; execute well defined change management plan | A new platform may affect the performance and response time of the dispatch centers initially |  | 2019-11-13 10:41 | anthony.leung@disney.com
Hosting in China Azure – new environment for International and SHDR IT teams | Risk | Open | 2019-09-10 |  |  | 1 | SHDR | Anthony Leung |  | 3 | 1 | 3 | Mitigate - Vendor to provide Azure Resource templates and key documentations; regular meetings with D3, Microsoft and EBS and SHDR IT teams to address issues | It will delay the infrastructure set up and configuration as tech teams are working on new tech environments |  | 2019-10-24 10:58 | nitin.x.bhatnagar.-nd@disney.com
Genetec and Easy Lobby integrations approach is not finalized among business teams | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Project sponsor to bring issue to business executives to address and provide final decision to align with EBS recommendation | It will delay the integration execution timeline and may increase the cost |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
Genetec Web API does not support vehicle BOLO alert | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Project sponsor to facilitate technical consultation between EBS and Genetec | It will delay the integration execution timeline and may increase the cost |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
EDH TRIRIGA integration – new work will not be starting until March 2020 | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Manually uploading location files from TRIRIGA to D3 initially to establish location hierarchy since locations do not change frequently | It will delay the integrations to TRIRIGA and over integration execution timeline |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
VPN Connectivity between Corporate D3 and Burbank data center; SHDR D3 and SHDR data center – does not meet performance requirements | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Performance testing to determine if VPN response time is acceptable | Increase cost to use dedicated express route connection |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
Project coordination among multiple organizations that are geographically disperse | Risk | Open | 2019-09-10 |  |  | 1 | Aulani SHDR | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Full time project manager to schedule project meetings to accommodate schedules as needed. Microsoft Teams Project site will allow for real-time collaboration. | May impact project timeline |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
Scope is not well defined - specific operations requirements from a diverse user group community may extend configuration effort | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Project team will review regularly with executive committees to prioritize configuration requirements to fit within the project time frame | Extends project timeline and increase costs |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
Resource constraint – extensive effort is required to gather large volume of operations specifications | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Business process sub-committees will be formed to define business requirements ahead of time and a dedicated business analyst will be involved in requirements, testing, training and configuration | It will delay the configuration phase and business users may not have all workflows needed for their operations |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
Overly optimistic project schedule | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Mitigate - Active project tracking to assure schedule slips to be detected early; interactive delivery allows for core functionality | Major functionality cannot be delivered per planned schedule requiring additional resources hours to complete |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
No standardized business processes and workflows | Risk | Open | 2019-09-10 |  |  | 1 | All | Anthony Leung |  | 2 | 1 | 2 | Accept / Mitigate - Define the foundational process but allow for variations through template configurations for different user groups | Value of consolidated threat analysis and reporting not realized |  | 2019-11-01 08:51 | nitin.x.bhatnagar.-nd@disney.com
Share the list of Business contacts for business requirements and definition with Nitin | Action Item | Closed | 2019-10-24 |  |  | 1 | All | Nitin Bhatnagar | Shelagh Sayers | 2 | 2 | 4 |  |  |  | 2019-11-07 15:13 | nitin.x.bhatnagar.-nd@disney.com
Business to work on Incident Types with GSCC operations-level staff | Action Item | In Progress | 2019-10-31 |  |  | 1 | GSCC | Liz Robert | Shelagh Sayers | 3 | 1 | 3 |  |  | 11/12: Shelagh continuing to work on this item. Very close to being done. | 2019-11-13 13:17 | nitin.x.bhatnagar.-nd@disney.com
Define the Perspective data to migrate | Action Item | Open | 2019-11-11 |  |  | 1 |  | Anthony Leung | Shelagh Sayers | 3 | 1 | 3 |  |  |  | 2019-11-11 15:55 | nitin.x.bhatnagar.-nd@disney.com
Additional requirements for GlobalSecurity web site for employees to submit request and report (incident types not aligned. It is out of scope. | Risk | Open | 2019-11-14 |  |  | 1 | GSCC GSI WCOPs | Anthony Leung | Liz Robert | 3 | 1 | 3 |  |  |  | 2019-11-13 10:41 | anthony.leung@disney.com

## Comments
Row 1 | See attached Data Retention Policy shared by Shelagh on 10/15/2019. Source: Laurie Carpenter, the Director of Records and Information Management | Nitin Bhatnagar | 10/23/19 3:54 PM